## Instructions
Cloud Platforms (combined) roadmap
Maintained by the delivery manager. Update monthly, and at least every quarter.
How to update
Step 1 | On the Product Area tab, pick your product area code (cell B1, e.g. AZC) and put your name and today's date. In a combined file that covers several areas, leave B1 blank and set Product area on each initiative row.
Step 2 | On the Initiatives tab, add or update one row per initiative. Use the dropdowns.
Step 3 | Every time you look at a row, set Last reviewed to today, even if nothing changed.
Step 4 | If an initiative is At risk or Off track, write a Risk note: what is wrong and what you are doing about it.
Step 5 | On the Milestones tab, add 1-3 milestones per committed initiative. Add a Review gate where leadership should check impact.
Step 6 | Preview: drag this file onto the roadmap dashboard ("Preview a roadmap file"). Fix anything in the Data quality tab.
Step 7 | Save the file in the shared roadmap folder by the monthly cutoff.
Legend
Yellow cell | Fill this in.
EXAMPLE row | Shows the expected format. It is ignored; overwrite or delete it.
Red date | End date is before the start date.
Amber date | Not reviewed in over 30 days.
Field guide
Product area | Area code from the dropdown. Needed when one file holds several areas. | AZC
ID | Unique ID: product area code + number, e.g. AZC-01. Never reuse or renumber an ID. | AZC-01
Initiative | Short name a leader would recognize. | Kubernetes platform GA
Strategic theme | Which enterprise theme it moves. See the Reference tab. | Unified multi-cloud governance
Horizon | Commit / Plan / Explore. See the Reference tab. | Commit
Status | Delivery health right now. | On track
Start / End date | Planned window. Move the end date if the plan changes, and say why in Risk note. | 9/1/2026
Jira epic | Epic key only, not the URL. | PLAT-140
Depends on | IDs this needs first, separated by semicolons. Can be another area's ID. | CLD-01; IAM-01
Last reviewed | Date you last checked this row. | 10/7/2026
Notes | Working notes, sources, assumptions. Not shown on the dashboard. | Dates assumed; confirm with PO

## Product Area
Product area code |  | Pick from the list. Leave blank in a combined file; use the Product area column instead.
Product area name | Combined: AZC, GCP, OCI, AVD, SCM, OBH | For reference only. The enterprise setup decides the official name.
Updated by | Draft from weekly PO updates (9/16, 9/23, 10/7); AVD from AVD FY27 Milestones page (10/19) | Your name.
Last updated | 2026-10-19 | Date you finished this update.

## Initiatives
ID | Product area | Initiative | Strategic theme | Horizon | Status | Start date | End date | Owner | Summary | Jira epic | Depends on | Risk note | Last reviewed | Notes (not shown on dashboard)
AZC-01 | AZC | AIQA onboarding: Azure AI Search & AI Document Intelligence | Expand hybrid & multi-cloud hosting | Commit | At risk | 2026-09-01 | 2026-12-31 |  | Get Azure AI Search and Azure AI Document Intelligence approved and enabled so the AIQA team can onboard to Azure Commercial. | CLDSPT-111655 |  | SIA ticket CLDSPT-111655 has been ON HOLD with SecOps since at least 9/16. Document Intelligence (SPA-2589) is still in SSO review. Need a SecOps decision date. | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Tracking SPA-2583 (AI Search, SM approved) and SPA-2589 (Doc Intelligence, SSO review). Source: COMET<>CMS PO updates 9/16, 9/23, 10/7.
AZC-02 | AZC | OPOLE proof of concept (ECSG data) | Expand hybrid & multi-cloud hosting | Plan | On track | 2026-09-16 | 2026-12-31 |  | Stand up infrastructure for the OPOLE PoC on ECSG data with Microsoft, then document the roadmap for the remaining priorities. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Initial planning/discovery noted 9/16; MSFT demo held 9/24; follow-up meeting pending (10/7). Source: COMET<>CMS PO updates.
AZC-03 | AZC | Azure Synapse Analytics service approval | Expand hybrid & multi-cloud hosting | Commit | At risk | 2026-09-23 | 2026-12-31 |  | Approve and enable Azure Synapse Analytics (Spark pools, dedicated SQL pool, Private Link Hub) for production use. | CLDSPT-115457 |  | SIA CLDSPT-115457 is ON HOLD with SecOps; SPA-2485 is in ISSO review. No decision date yet. | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. SIA raised by 9/23. Source: COMET<>CMS PO updates 9/23, 10/7.
AZC-04 | AZC | EOC integration of GSS services | Unified multi-cloud governance | Commit | On track | 2026-08-01 | 2026-12-31 |  | Integrate the remaining applicable GSS services with the EOC so Azure Commercial is monitored the same way as the other clouds. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Zscaler and Centralized Firewall EOC integration completed (reported 9/09). Remaining services not listed in the updates. Source: COMET<>CMS PO updates.
AZC-05 | AZC | Azure West (second region) availability | Production readiness & operations | Plan | On track | 2026-09-01 | 2027-03-31 |  | Agree level of effort and timelines with GSS teams to operationalize Azure Commercial services in a second region (Azure West). |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Being tracked in the IUSG weekly call; no committed timeline yet. Source: COMET<>CMS PO updates 9/16, 9/23, 10/7.
AZC-06 | AZC | Entra ID access management (ENTRA_CLOUD_USER job code) | Secure access & compliance | Commit | On track | 2026-09-01 | 2026-12-31 |  | Provision users into Entra ID through the new EUA job code (ENTRA_CLOUD_USER) as part of production readiness. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. New provisioning workflow verified (reported 9/16). Next step after verification not stated. Source: COMET<>CMS PO updates.
AZC-07 | AZC | Cloud Computing Guide (CCG) documentation handoff | Production readiness & operations | Commit | On track | 2026-09-01 | 2026-12-31 |  | Finalize Azure Commercial CCG documents and hand them to the CSS team for publishing. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Ongoing handoff. Source: COMET<>CMS PO updates.
GCP-01 | GCP | EQRS production onboarding | Expand hybrid & multi-cloud hosting | Commit | Done | 2026-07-01 | 2026-09-16 |  | Bring EQRS to production in GCP. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Reported PROD Ready by 9/16. EQRS will need to move to the revised access management approach later (see GCP-08). Source: COMET<>CMS PO updates 9/16-10/7.
GCP-02 | GCP | GCP service approvals (SIAs) for ADO workloads | Secure access & compliance | Commit | At risk | 2026-09-01 | 2026-12-31 |  | Get SecOps decisions on the GCP services ADOs have requested, so they can move from non-prod to prod. | CLDSPT-112641 |  | Three SIAs ON HOLD with SecOps, two in backlog. Cloud Build has been on hold since at least 9/16 and also blocks Observability Hub (OBH-03). | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Open SIAs on 10/7: Service Directory CLDSPT-114389 (ON HOLD), Cloud Build CLDSPT-112641 (ON HOLD), Workflows API CLDSPT-115742 (ON HOLD), Knowledge Catalog CLDSPT-115656 (backlog), VM Migration CLDSPT-116513 (backlog). All but VM Migration are enabled in ADO non-prod with ADO ISSO/BO approval. 9/16: Parameter Manager, Database Migration Service and Storage Transfer not approved at GSS level; ADOs may enable in their own boundary with ISSO/BO risk acceptance. Source: COMET<>CMS PO updates.
GCP-03 | GCP | Agentic Data Cloud project for EADG/IDR (Knowledge Catalog + Snowflake) | Expand hybrid & multi-cloud hosting | Commit | On track | 2026-09-15 | 2026-12-31 |  | New GCP project with Knowledge Catalog enabled and PrivateLink connectivity to Snowflake in AWS. | FY26INIT-1176 | GCP-02 |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. ONBI-14306 tenant provisioning DONE; CPT-6984 funding APPROVED; project created (FY26INIT-1176 IN PROGRESS); CLDSPT-116097 Snowflake connectivity RESOLVED; Knowledge Catalog SIA CLDSPT-115656 in backlog. Source: COMET<>CMS PO updates 9/23, 10/7.
GCP-04 | GCP | CCIC sandbox project | Expand hybrid & multi-cloud hosting | Commit | On track | 2026-09-23 | 2026-10-31 |  | Provision a GCP sandbox project for the CCIC team and hand it over after network testing. | CLDSPT-116263 |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. ONBI-14712 tenant provisioning DONE; CLDSPT-116263 project created, testing network before handover. Source: COMET<>CMS PO updates 10/7.
GCP-05 | GCP | Pre-handover checks for new GCP projects | Unified multi-cloud governance | Commit | On track | 2026-09-01 | 2026-11-30 |  | Automated checks run before a GCP project is handed to an ADO, built into the SPA workflow. | FY26INIT-1041 |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Scripts integrated with the SPA workflow and being tested (9/23, 10/7). Source: COMET<>CMS PO updates.
GCP-06 | GCP | Billing visibility for ADOs | Unified multi-cloud governance | Plan | Not started | 2026-11-01 | 2027-01-31 |  | Let ADOs see billing information in their own GCP projects. | FY26INIT-1084 |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. FY26INIT-1084 still TO DO on 10/7. Source: COMET<>CMS PO updates.
GCP-07 | GCP | EOC integration of GSS services | Unified multi-cloud governance | Commit | On track | 2026-08-01 | 2026-12-31 |  | Integrate the remaining applicable GSS services with the EOC. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Zscaler and Centralized Firewall done; remaining services not listed. Source: COMET<>CMS PO updates.
GCP-08 | GCP | Entra ID access management migration | Secure access & compliance | Commit | On track | 2026-09-01 | 2026-12-31 |  | Provision users into Entra ID through the ENTRA_CLOUD_USER job code, and move existing tenants (e.g. EQRS) to it. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Workflow validated; EQRS migration still to come. Source: COMET<>CMS PO updates.
GCP-09 | GCP | GCP West (second region) availability | Production readiness & operations | Plan | On track | 2026-09-01 | 2027-03-31 |  | Agree the region and readiness plan for GCP West with stakeholders. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Hot item 10/7: finalizing region; stakeholder meeting with Chris Vee on 10/13. Source: COMET<>CMS PO updates.
GCP-10 | GCP | GCP documentation (CCG and cloud.cms.gov) | Production readiness & operations | Commit | On track | 2026-09-01 | 2026-12-31 |  | Unify GCP documentation and publish it through the COMMS team. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. FY26INIT-1097 unified docs DONE (9/23); CCG updates with COMMS ongoing. Source: COMET<>CMS PO updates.
OCI-01 | OCI | OCI Day 2 services | Production readiness & operations | Commit | At risk | 2026-07-01 | 2026-10-15 |  | Operational (Day 2) services for OCI: backup automation, SMTP, patching, logging and DNS. |  |  | Target date has moved twice (8/31 -> 9/30 -> 10/15). Depends on Oracle fixes with no committed dates. | 2026-10-07 | Start date placeholder. Target moved 8/31 (9/16 update) -> 9/30 (9/23) -> 10/15 (10/7). SMTP production ready 10/7; backup functions completed 10/7 (prod function pending). Custom Software Source fix in OS Management Hub 3.8 (Oracle support case). Internal DNS testing was blocked on a security change request (9/16). Source: COMET<>CMS PO updates.
OCI-02 | OCI | Oracle enhancement requests (logging, reboot, enterprise patching) | Production readiness & operations | Plan | At risk | 2026-09-01 | 2027-03-31 |  | Get committed delivery dates from Oracle for the logging, reboot and enterprise patching enhancements. |  |  | Oracle feature and enhancement requests have no committed delivery dates, which leaves long-term patching and operations uncertain. | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Oracle to give updated ETA (logging), confirm roadmap (reboot), explore earlier release (patching). Source: COMET<>CMS PO updates.
OCI-03 | OCI | Security monitoring: audit trail, alerting, threat detection | Secure access & compliance | Commit | On track | 2026-08-01 | 2026-10-31 |  | Audit trail, alerting and threat detection notifications working for SecOps and the SOC. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. SecOps confirmed functioning (9/23, 10/7); minor field sorting tweaks need SOC input. Source: COMET<>CMS PO updates.
OCI-04 | OCI | Datadog monitoring for OCI Government Cloud | Unified multi-cloud governance | Explore | On track | 2026-10-01 | 2026-12-31 |  | Evaluate the Datadog OCI Government Cloud integration to monitor network resources and route alerts to the EOC, like the other clouds. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Being evaluated in the non-prod connectivity compartment (10/7). Source: COMET<>CMS PO updates.
OCI-05 | OCI | Oracle Database@AWS (OCI Commercial tenancy) | Expand hybrid & multi-cloud hosting | Commit | On track | 2026-09-01 | 2026-12-31 |  | Lightweight OCI Commercial tenancy for Oracle Database@AWS that meets security, compliance and monitoring obligations, including log shipping to Cribl. | CLDSPT-115520 |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Security review defined compliance boundary; shared GSS compartment approved (CLDSPT-115520); logging VCN and Cloudflare VPN created, testing pending; DOOM access granted (CLDSPT-115181). Open question: does the tenancy support all logging services, or is a new subscription (CPT approval) needed? Source: COMET<>CMS PO updates.
OCI-06 | OCI | ExaCC Ashburn ADB pilot | Expand hybrid & multi-cloud hosting | Commit | At risk | 2026-08-01 | 2026-10-30 |  | Close out the non-prod Autonomous Database pilot on ExaCC Ashburn: EUA/EFT workload migrations, shared services integration and a repeatable process. |  |  | Blocked on network connectivity between the Ashburn and Kent data centers and ExaCC Ashburn; IaaS is still working on the approach (10/6). Pilot dates are now TBD. | 2026-10-07 | Start date placeholder. Dates moved: EUA/EFT migrations 9/18 -> TBD; process doc 9/21 -> 9/30 -> 10/26; shared services 9/30 -> 10/30; MiSP non-prod onboarding 9/25 -> TBD. Oracle SRs 4-0003803176 (resolved) and 4-0003830164 (under review). Source: COMET<>CMS PO updates.
OCI-07 | OCI | ExaCC Phoenix deployment | Expand hybrid & multi-cloud hosting | Commit | On track | 2026-09-01 | 2026-11-30 |  | Install and validate ExaCC equipment in Phoenix. |  |  |  | 2026-10-07 | Start date placeholder. Network installation and onsite validation started (9/23). Source: COMET<>CMS PO updates.
AVD-01 | AVD | AVD Operations in a Production Ready State | Production readiness & operations | Commit | On track | 2026-09-09 | 2027-09-30 |  | Patching, backup, golden image, CrowdStrike, vulnerability scanning, autoscaling, DR, change management and CCG updates. |  |  | Patching owner TBD (Citrix patches its own; decide with MiSP). Golden image approach pending with the Citrix team and SecOps. CrowdStrike: CLDSPT-114612 awaiting SecOps feedback. Disaster recovery blocked until the Azure West region is complete. Vulnerability scanning waits on Multi Session Host Pools (AVD-05). | 2026-10-19 | Source: AVD FY27 Milestones page (19 Oct 2026) via AVD FY27 Roadmap DRAFT 2. Status and theme are not in the source; carried over from the 10/7 PO update - confirm with the DM.
AVD-02 | AVD | AVD End User Support Services Operationalized | Production readiness & operations | Commit | On track | 2026-08-25 | 2027-03-31 |  | Support model (CLDSPT, EOC, Help Desk, Tier 2, user manual, training) ready for users. |  |  | Dependencies past their needed-by date: SRE Team EOC workbook items (Datadog integration, alerts, Splunk On-call), needed 8/28; CMS Help Desk / Nerdio CSM KBA approvals, agent trainings and SNOW integration, needed 9/10. | 2026-10-19 | Source: AVD FY27 Milestones page (19 Oct 2026) via AVD FY27 Roadmap DRAFT 2. Status and theme are not in the source; carried over from the 10/7 PO update - confirm with the DM.
AVD-03 | AVD | AVD Onboarding Process Established | Production readiness & operations | Commit | On track | 2026-09-01 | 2026-11-06 |  | Repeatable AVD onboarding: Jira project, ONBI integration, job codes. |  |  |  | 2026-10-19 | Source: AVD FY27 Milestones page (19 Oct 2026) via AVD FY27 Roadmap DRAFT 2. Status and theme are not in the source; carried over from the 10/7 PO update - confirm with the DM.
AVD-04 | AVD | VDI User Migrations | Expand hybrid & multi-cloud hosting | Commit | On track | 2027-01-04 | 2027-07-26 |  | Wave 0 validation (Jan 2027) through Wave 6 (Jul 2027), about 1,045 users combined. |  |  |  | 2026-10-19 | Source: AVD FY27 Milestones page (19 Oct 2026) via AVD FY27 Roadmap DRAFT 2. Status and theme are not in the source; carried over from the 10/7 PO update - confirm with the DM.
AVD-05 | AVD | AVD Feature Enhancements | Secure access & compliance | Commit | On track | 2026-08-25 | 2027-06-30 |  | Network, security and monitoring features (ZCC/Cloudflare, MFA, RTM, portal, host pools). |  |  | ZCC vs Cloudflare One decision blocked until the Cloudflare One POC is live. ECIS dependencies past their needed-by date: MFA setup (needed 8/25) and RTM permissions (needed 9/16). Network monitoring feasibility TBD. | 2026-10-19 | Source: AVD FY27 Milestones page (19 Oct 2026) via AVD FY27 Roadmap DRAFT 2. Status and theme are not in the source; carried over from the 10/7 PO update - confirm with the DM.
SCM-01 | SCM | TLS 1.3 adoption dashboards | Secure access & compliance | Commit | On track | 2026-09-01 | 2026-12-31 |  | Splunk dashboards that show TLS 1.3 adoption across AWS, Azure, GCP and on-prem. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. First iteration (ELB) 9/23; consolidated AWS CloudFront + ELB dashboard with listener and cipher columns 10/7. Next: TLS version and cipher filters; Azure and GCP dashboards; on-prem needs Splunk DC access and federated search. Source: COMET<>CMS PO updates.
SCM-02 | SCM | VPCConf/Cloudy integration (IP to cloud account lookup) | Unified multi-cloud governance | Commit | On track | 2026-09-16 | 2026-12-31 |  | Look up which CSP and account an IP address belongs to, using VPCConf data in Splunk. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Kickoff 9/16; S3 bucket and IAM role delivered 9/23; export landing in Observability Hub account 10/7. Next: ingest and build lookup table, then a simple IP lookup app. Source: COMET<>CMS PO updates.
SCM-03 | SCM | Azure and GCP log data validation with CCIC/SOC | Unified multi-cloud governance | Commit | On track | 2026-09-01 | 2026-12-31 |  | CCIC/SOC validates Azure and GCP logs in Splunk, and custom log collection is documented in the CCG. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Non-descriptive fields traced to Cribl Search normalizing only for Splunk Cloud, not ITOPS; MiSP normalized both. CCG for Azure/GCP custom log collection pending COMMS review and CMS approval. Source: COMET<>CMS PO updates.
SCM-04 | SCM | Splunk Cloud cost estimate | Unified multi-cloud governance | Commit | On track | 2026-09-01 | 2026-11-30 |  | Cost comparison for Splunk Cloud scenarios, including Splunk ITOPS and Splunk DC. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. SplunkPS delivered its estimate to Chris V. (by 10/7). Waiting on MiSP for ITOPS and DC costs. Source: COMET<>CMS PO updates.
SCM-05 | SCM | VPC/VNET flow logs to SDL | Unified multi-cloud governance | Commit | On track | 2026-09-16 | 2027-03-31 |  | Ingest cloud flow logs into the Security Data Lake, starting with GCP. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. SDL started GCP flow log ingestion (10/7); SDL plans an instance in GCP (funding to check). Also: route VPC flow logs to Cribl with MiSP; centralized OCI Object Storage with the OCI team. Source: COMET<>CMS PO updates.
SCM-06 | SCM | Splunk DBConnect proof of concept (CCIC/SOC to SDL) | Unified multi-cloud governance | Explore | On track | 2026-09-16 | 2026-12-31 |  | Connect the SOC Splunk instance to the SDL with DBConnect. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Service account received; CCIC/SOC installing JRE prerequisites (10/7). Source: COMET<>CMS PO updates.
SCM-07 | SCM | Splunk Cloud migration roadmap | Unified multi-cloud governance | Plan | At risk | 2026-09-01 | 2026-12-31 |  | Finalize the Splunk Cloud migration roadmap. |  |  | Waiting on the MiSP Logging team's plan to retrofit Cribl Search in AWS since 9/23; roadmap cannot be finalized until then. | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Draft roadmap done (9/09); depends on the Cribl task for routing AWS logs. Open question: who owns ES and Core (POC/responsibility). Source: COMET<>CMS PO updates.
OBH-01 | OBH | Application onboarding to Observability Hub | Unified multi-cloud governance | Commit | On track | 2026-08-01 | 2026-12-31 |  | Onboard infrastructure services and MEF applications to Observability Hub, with correct Datadog tags. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. AD (Outpost) onboarded (9/16); SMTP (Outpost) onboarded (by 9/23); SRE onboarding 6 MEF apps (APS, eCHIMP, MARx, MEPBS, NGD, NPPES); teams asked to update Datadog tags. Source: COMET<>CMS PO updates (PI-2 plan).
OBH-02 | OBH | Observability Hub CCG pages | Production readiness & operations | Commit | On track | 2026-09-01 | 2026-11-30 |  | Publish "Introduction to Observability Hub" and "Onboarding to Observability Hub" in the CCG. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Drafts with COMMS; publishing in progress (9/23, 10/7). Source: COMET<>CMS PO updates.
OBH-03 | OBH | Forward ESS events and summary metrics from Azure and GCP | Unified multi-cloud governance | Commit | At risk | 2026-08-01 | 2026-12-31 |  | Send ESS events and summary metrics from Azure and GCP to Observability Hub. |  | GCP-02 | GCP deployment has waited on the GCP Cloud Build SIA since at least 9/16 (see GCP-02). Azure validation still pending. | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. Azure solution developed, validation pending. GCP solution deployment by MiSP (DOOMS) to one account waiting on the Cloud Build SIA. Source: COMET<>CMS PO updates.
OBH-04 | OBH | BaseCAMP lookup tables and EOC dashboard | Unified multi-cloud governance | Commit | On track | 2026-08-15 | 2026-11-30 |  | Use BaseCAMP data (role- and application-centric lookup tables) in the EOC dashboard; Datadog Monitoring Dashboard v1.3. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. BaseCAMP data in ObsHub and first lookup table (9/16); two tables created (by 9/23); next: apply to EOC dashboard. Source: COMET<>CMS PO updates.
OBH-05 | OBH | Cribl Replay and AI usage evaluation | Unified multi-cloud governance | Explore | On track | 2026-09-01 | 2026-12-31 |  | Evaluate Cribl Replay and AI use in CSP monitoring services and Splunk. |  |  |  | 2026-10-07 | Start/end dates are placeholders (not in the updates); confirm with the PO. MiSP finished evaluating Cribl Replay; demo session pending. Source: COMET<>CMS PO updates.

## Milestones
Initiative ID | Milestone | Date | Type | Done | Jira epic | Start date | Feature ID | Team
AZC-01 | Azure AI Search: SPA-2583 SM approved | 2026-09-16 | Decision | Yes
AZC-01 | Azure AI Document Intelligence: SPA-2589 SSO review complete |  | Decision | No
AZC-01 | Multi-cloud hosting goal: 2+ CMS workloads in Azure Commercial | 2026-09-30 | Review gate | No
AZC-02 | Microsoft demo of OPOLE PoC (ECSG data) | 2026-09-24 | Pilot | Yes
AZC-02 | Follow-up: document roadmap for remaining priorities |  | Decision | No
AZC-03 | SecOps SIA decision on Synapse (SPA-2485) |  | Decision | No
AZC-04 | EOC integration: Zscaler and Centralized Firewall | 2026-09-09 | Release | Yes
AZC-04 | EOC integration complete for remaining GSS services |  | Release | No
AZC-05 | LOE and timeline agreed with GSS teams |  | Decision | No
AZC-06 | Entra ID provisioning workflow (ENTRA_CLOUD_USER) verified | 2026-09-16 | Release | Yes
GCP-01 | EQRS production ready | 2026-09-16 | Release | Yes
GCP-02 | SecOps decision: Parameter Manager, DMS, Storage Transfer (ADO boundary only) | 2026-09-16 | Decision | Yes
GCP-02 | SecOps decision on Cloud Build SIA (CLDSPT-112641) |  | Decision | No | CLDSPT-112641
GCP-03 | Funding approved (CPT-6984) | 2026-09-23 | Decision | Yes | CPT-6984
GCP-03 | Project created and Snowflake connectivity established | 2026-10-07 | Release | Yes | CLDSPT-116097
GCP-03 | Knowledge Catalog SIA decision (CLDSPT-115656) |  | Decision | No | CLDSPT-115656
GCP-04 | Sandbox handed over to CCIC |  | Release | No
GCP-09 | Stakeholder meeting to finalize GCP West region | 2026-10-13 | Decision | No
GCP-10 | GCP documentation unified (FY26INIT-1097) | 2026-09-23 | Release | Yes | FY26INIT-1097
GCP-01 | Multi-cloud hosting goal: 2+ CMS workloads in GCP | 2026-09-30 | Review gate | No
OCI-01 | SMTP production ready | 2026-10-07 | Release | Yes
OCI-01 | OCI Day 2 services complete | 2026-10-15 | Release | No
OCI-05 | Shared GSS compartment approved | 2026-09-23 | Decision | Yes | CLDSPT-115520
OCI-05 | Decision: separate subscription for logging (CPT approval)? |  | Decision | No
OCI-06 | Connectivity approach meeting (Ashburn/Kent to ExaCC) | 2026-10-06 | Decision | Yes
OCI-06 | Document repeatable migration/operational process | 2026-10-26 | Release | No
OCI-06 | Ashburn shared services integrated (monitoring, logging, backup, security, ops) | 2026-10-30 | Release | No
OCI-06 | EUA/EFT workload migrations and pilot testing complete |  | Pilot | No
OCI-07 | Network installation and onsite validation started | 2026-09-23 | Release | Yes
OCI-07 | Confirm Oracle build/ship date; schedule equipment install | 2026-10-16 | Decision | No
OCI-07 | Install Phoenix ExaCC equipment | 2026-11-15 | Release | No
OCI-05 | Multi-cloud hosting goal: 2+ CMS workloads in OCI | 2026-09-30 | Review gate | No
AVD-01 | Patching - OS / System |  | Release | No |  |  | AVD-01.1 | MiSP
AVD-01 | Backup - Data Protect | 2026-11-06 | Release | No |  | 2026-10-19 | AVD-01.2 | IaaS
AVD-01 | Golden Image Management | 2026-12-31 | Release | No |  | 2026-10-19 | AVD-01.3 | SecOps
AVD-01 | CrowdStrike Integration | 2026-10-30 | Release | No |  | 2026-09-09 | AVD-01.4 | SecOps
AVD-01 | Vulnerability Scanning | 2027-09-30 | Release | No |  | 2027-07-01 | AVD-01.9 | COMET / SecOps
AVD-01 | Autoscaling | 2026-09-24 | Release | No |  | 2026-09-24 | AVD-01.5 | COMET
AVD-01 | Disaster Recovery |  | Release | No |  |  | AVD-01.6 | IaaS / COMET
AVD-01 | Change Management | 2027-03-31 | Release | No |  | 2027-01-01 | AVD-01.7 | COMET
AVD-01 | CCG Updates | 2027-03-31 | Release | No |  | 2027-01-01 | AVD-01.8 | COMET / CSS
AVD-02 | AVD CLDSPT Requests | 2026-10-23 | Release | No |  | 2026-09-16 | AVD-02.1 | COMET (Atlassian)
AVD-02 | EOC Integration | 2026-10-30 | Release | No |  | 2026-08-28 | AVD-02.2 | SRE Team
AVD-02 | CMS Help Desk | 2026-11-27 | Release | No |  | 2026-09-10 | AVD-02.3 | CMS Help Desk / Nerdio CSM
AVD-02 | Distribution List / Gov Delivery | 2026-12-04 | Release | No |  | 2026-08-25 | AVD-02.4 | COMET
AVD-02 | Cloud Tier 2 | 2027-03-31 | Release | No |  | 2027-01-01 | AVD-02.5 | COMET
AVD-02 | User Manual | 2027-03-31 | Release | No |  | 2027-01-01 | AVD-02.6 | COMET
AVD-02 | Customer Support Team Training | 2027-03-31 | Release | No |  | 2027-01-01 | AVD-02.7 | COMET / CSS
AVD-03 | Onboarding Process | 2026-11-06 | Release | No |  | 2026-09-01 | AVD-03.1 | COMET
AVD-04 | Wave 0 - Validation only, no real users | 2027-01-04 | Review gate | No |  | 2027-01-04 | AVD-04.1 | COMET
AVD-04 | Wave 1 - Admin Desktop (10) | 2027-02-08 | Release | No |  | 2027-02-08 | AVD-04.2 | COMET
AVD-04 | Wave 2 - ECIS + Employees Desktop (60) | 2027-03-08 | Release | No |  | 2027-03-08 | AVD-04.3 | COMET
AVD-04 | Wave 3 - Developers Desktop (30, 8 vCPU/32GB) | 2027-04-05 | Release | No |  | 2027-04-05 | AVD-04.4 | COMET
AVD-04 | Wave 4 - RTI Desktop (80) | 2027-05-17 | Release | No |  | 2027-05-17 | AVD-04.5 | COMET
AVD-04 | Wave 5 - SAS PROD + Pre-Dev + VAL (260) | 2027-06-28 | Release | No |  | 2027-06-28 | AVD-04.6 | COMET
AVD-04 | Wave 6 - Contractors + Contractors 50G (605) | 2027-07-26 | Release | No |  | 2027-07-26 | AVD-04.7 | COMET
AVD-05 | Zscaler Cloud Connector (ZCC) or Cloud Connector | 2027-03-31 | Decision | No |  | 2027-01-01 | AVD-05.1 | NetOps
AVD-05 | Real Time Monitoring | 2026-10-08 | Release | No |  | 2026-09-16 | AVD-05.2 | ECIS
AVD-05 | MFA | 2026-10-30 | Release | No |  | 2026-08-25 | AVD-05.3 | ECIS
AVD-05 | AVD Portal | 2027-03-31 | Release | No |  | 2027-01-01 | AVD-05.4 | COMET
AVD-05 | Multi Session Host Pools | 2027-06-30 | Release | No |  | 2027-04-01 | AVD-05.5 | COMET
AVD-05 | Network Monitoring |  | Release | No |  |  | AVD-05.6 | NetOps
SCM-01 | Consolidated AWS TLS compliance dashboard (CloudFront + ELB) | 2026-10-07 | Release | Yes
SCM-01 | Azure and GCP TLS dashboards |  | Release | No
SCM-02 | VPCConf export landing in Observability Hub S3 bucket | 2026-10-07 | Release | Yes
SCM-02 | IP-to-account lookup table and app |  | Release | No
SCM-03 | CCG: Azure and GCP custom log collection approved by CMS |  | Decision | No
SCM-04 | SplunkPS cost estimate delivered | 2026-10-07 | Decision | Yes
SCM-05 | SDL starts GCP flow log ingestion | 2026-10-07 | Release | Yes
SCM-05 | Funding decision: SDL instance in GCP |  | Decision | No
SCM-07 | MiSP plan for Cribl Search retrofit in AWS received |  | Decision | No
OBH-01 | AD (Outpost) onboarded | 2026-09-16 | Release | Yes
OBH-01 | SMTP (Outpost) onboarded | 2026-09-23 | Release | Yes
OBH-01 | 6 MEF applications onboarded |  | Release | No
OBH-03 | Azure ESS forwarding validated |  | Release | No
OBH-03 | GCP ESS forwarding deployed to first account |  | Release | No
OBH-04 | BaseCAMP lookup tables created | 2026-09-23 | Release | Yes
OBH-04 | BaseCAMP lookup applied to EOC dashboard |  | Release | No
OBH-05 | Cribl Replay demo |  | Decision | No

## Reference
Theme code | Theme | Description | Horizon | Meaning | Status | Meaning | Milestone type | Area code | Product area
GOV | Unified multi-cloud governance | OIT Tech Pulse goal: unified governance model for GCP, OCI and Azure Commercial with consistent policy enforcement, cost visibility and performance monitoring (target Aug 2026). | Commit | Scope and dates are firm. We track against them. | Not started | Work has not begun. | Release | AZC | Azure Commercial
MCH | Expand hybrid & multi-cloud hosting | OIT Tech Pulse goal: host at least two CMS applications or infrastructure workloads in each of GCP, OCI and Azure Commercial using best-fit placement (target Sep 2026). | Plan | Direction is set. Dates are indicative. | On track | Expected to finish by the end date. | Pilot | GCP | Google Cloud Provider
OPS | Production readiness & operations | Services are production ready: EOC monitoring, support model, documentation, backup and a second region. | Explore | Options under evaluation, not commitments. | At risk | Could miss the end date without action. Add a risk note. | Review gate | OCI | Oracle Cloud Infrastructure
SEC | Secure access & compliance | Identity and access, security approvals (SIA), audit findings and protocol remediation. |  |  | Off track | Will miss the end date. Add a risk note with the recovery plan. | Decision | AVD | Azure Virtual Desktop
DPT | Developer platform & tooling | DevOps platform, Agile tools and automation that teams build and deliver with. |  |  | Done | Finished. |  | SCM | Splunk Cloud Modernization
[8 empty] | OBH | Observability Hub
[8 empty] | CAH | Cloud Automation + Helix
Themes and product areas come from the enterprise setup. Ask the Director to change them. | [7 empty] | CMG | Cloud Migration
[8 empty] | CAD | Cloud AD
[8 empty] | DVO | Cloud DevOps
[8 empty] | AGT | Agile Tools