## Instructions
Observability roadmap
Maintained by the delivery manager. Update monthly, and at least every quarter.
How to update
Step 1 | On the Product Area tab, pick your product area code (cell B1, e.g. CLD) and put your name and today's date.
Step 2 | On the Initiatives tab, add or update one row per initiative. Use the dropdowns.
Step 3 | Every time you look at a row, set Last reviewed to today, even if nothing changed.
Step 4 | If an initiative is At risk or Off track, write a Risk note: what is wrong and what you are doing about it.
Step 5 | On the Milestones tab, add 1-3 milestones per committed initiative. Add a Review gate where leadership should check impact.
Step 6 | Preview: drag this file onto the roadmap dashboard ("Preview a roadmap file"). Fix anything in the Data quality tab.
Step 7 | Save the file in the shared roadmap folder by the monthly cutoff.
Legend
Yellow cell | Fill this in.
EXAMPLE row | Shows the expected format. It is ignored; overwrite or delete it.
Red date | End date is before the start date.
Amber date | Not reviewed in over 30 days.
Field guide
ID | Unique ID: product area code + number, e.g. OBS-01. Never reuse or renumber an ID. | OBS-01
Initiative | Short name a leader would recognize. | Kubernetes platform GA
Strategic theme | Which enterprise theme it moves. See the Reference tab. | Accelerate delivery
Horizon | Commit / Plan / Explore. See the Reference tab. | Commit
Status | Delivery health right now. | On track
Start / End date | Planned window. Move the end date if the plan changes, and say why in Risk note. | 9/1/2026
Jira epic | Epic key only, not the URL. | PLAT-140
Depends on | IDs this needs first, separated by semicolons. Can be another area's ID. | CLD-01; IAM-01
Last reviewed | Date you last checked this row. | 10/7/2026

## Product Area
Product area code | OBS | Pick from the list. Set once.
Product area name | Observability | For reference only. The enterprise setup decides the official name.
Updated by | Alicia Gomez | Your name.
Last updated |  | Date you finished this update.

## Initiatives
ID | Initiative | Strategic theme | Horizon | Status | Start date | End date | Owner | Summary | Jira epic | Depends on | Risk note | Last reviewed
OBS-01 | Unified logging & SLOs | Improve reliability | Commit | On track | 2026-08-17 | 2027-02-26 | Sam Ortiz | One logging pipeline and published SLOs for every tier-1 service. | OBS-3 |  |  | 2026-09-29
OBS-02 | Automated incident response | Improve reliability | Plan | Not started | 2027-03-01 | 2027-09-30 | Sam Ortiz | Runbook automation triggered by SLO burn alerts. |  | OBS-01 |  | 2026-09-29
OBS-03 | AIOps anomaly detection | Improve reliability | Explore | Not started | 2027-11-01 | 2028-03-31 | Alicia Gomez | Evaluate anomaly detection on the unified telemetry set. |  | OBS-01 |  | 2026-06-30

## Milestones
Initiative ID | Milestone | Date | Type | Done | Jira epic
OBS-01 | SLOs published for tier-1 | 2026-12-11 | Release | No
OBS-01 | Reliability review | 2027-03-31 | Review gate | No
OBS-02 | Auto-remediation pilot | 2027-06-15 | Pilot | No

## Reference
Theme code | Theme | Description | Horizon | Meaning | Status | Meaning | Milestone type | Area code | Product area
ACC | Accelerate delivery | Shorten the path from idea to production. | Commit | Scope and dates are firm. We track against them. | Not started | Work has not begun. | Release | CLD | Cloud Platform
REL | Improve reliability | Fewer failed changes, faster recovery. | Plan | Direction is set. Dates are indicative. | On track | Expected to finish by the end date. | Pilot | DSO | DevSecOps Pipelines
SEC | Strengthen security & compliance | Controls enforced in code, evidence on demand. | Explore | Options under evaluation, not commitments. | At risk | Could miss the end date without action. Add a risk note. | Review gate | IAM | Identity & Access
CST | Optimize cloud cost | Spend tracks value and is visible per team. |  |  | Off track | Will miss the end date. Add a risk note with the recovery plan. | Decision | DAT | Data Platform
[5 empty] | Done | Finished. |  | OBS | Observability
Themes and product areas come from the enterprise setup. Ask the Director to change them.