## Instructions
Observability Hub roadmap
Maintained by the delivery manager. Update monthly, and at least every quarter.
How to update
Step 1 | On the Product Area tab, pick your product area code (cell B1, e.g. AZC) and put your name and today's date. In a combined file that covers several areas, leave B1 blank and set Product area on each initiative row.
Step 2 | On the Initiatives tab, add or update one row per initiative. Use the dropdowns.
Step 3 | Every time you look at a row, set Last reviewed to today, even if nothing changed.
Step 4 | If an initiative is At risk or Off track, write a Risk note: what is wrong and what you are doing about it.
Step 5 | On the Milestones tab, add 1-3 milestones per committed initiative. Add a Review gate where leadership should check impact.
Step 6 | Preview: drag this file onto the roadmap dashboard ("Preview a roadmap file"). Fix anything in the Data quality tab.
Step 7 | Save the file in the shared roadmap folder by the monthly cutoff.
Legend
Yellow cell | Fill this in.
EXAMPLE row | Shows the expected format. It is ignored; overwrite or delete it.
Red date | End date is before the start date.
Amber date | Not reviewed in over 30 days.
Field guide
Product area | Area code from the dropdown. Needed when one file holds several areas. | OBH
ID | Unique ID: product area code + number, e.g. OBH-01. Never reuse or renumber an ID. | OBH-01
Initiative | Short name a leader would recognize. | Kubernetes platform GA
Strategic theme | Which enterprise theme it moves. See the Reference tab. | Unified multi-cloud governance
Horizon | Commit / Plan / Explore. See the Reference tab. | Commit
Status | Delivery health right now. | On track
Start / End date | Planned window. Move the end date if the plan changes, and say why in Risk note. | 9/1/2026
Jira epic | Epic key only, not the URL. | PLAT-140
Depends on | IDs this needs first, separated by semicolons. Can be another area's ID. | CLD-01; IAM-01
Last reviewed | Date you last checked this row. | 10/7/2026
Notes | Working notes, sources, assumptions. Not shown on the dashboard. | Dates assumed; confirm with PO

## Product Area
Product area code | OBH | Pick from the list. Leave blank in a combined file; use the Product area column instead.
Product area name | Observability Hub | For reference only. The enterprise setup decides the official name.
Updated by | Ashita Rajvanshi | Your name.
Last updated |  | Date you finished this update.

## Initiatives
ID | Product area | Initiative | Strategic theme | Horizon | Status | Start date | End date | Owner | Summary | Jira epic | Depends on | Risk note | Last reviewed | Notes (not shown on dashboard)

## Milestones
Initiative ID | Milestone | Date | Type | Done | Jira epic

## Reference
Theme code | Theme | Description | Horizon | Meaning | Status | Meaning | Milestone type | Area code | Product area
GOV | Unified multi-cloud governance | OIT Tech Pulse goal: unified governance model for GCP, OCI and Azure Commercial with consistent policy enforcement, cost visibility and performance monitoring (target Aug 2026). | Commit | Scope and dates are firm. We track against them. | Not started | Work has not begun. | Release | AZC | Azure Commercial
MCH | Expand hybrid & multi-cloud hosting | OIT Tech Pulse goal: host at least two CMS applications or infrastructure workloads in each of GCP, OCI and Azure Commercial using best-fit placement (target Sep 2026). | Plan | Direction is set. Dates are indicative. | On track | Expected to finish by the end date. | Pilot | GCP | Google Cloud Provider
OPS | Production readiness & operations | Services are production ready: EOC monitoring, support model, documentation, backup and a second region. | Explore | Options under evaluation, not commitments. | At risk | Could miss the end date without action. Add a risk note. | Review gate | OCI | Oracle Cloud Infrastructure
SEC | Secure access & compliance | Identity and access, security approvals (SIA), audit findings and protocol remediation. |  |  | Off track | Will miss the end date. Add a risk note with the recovery plan. | Decision | AVD | Azure Virtual Desktop
DPT | Developer platform & tooling | DevOps platform, Agile tools and automation that teams build and deliver with. |  |  | Done | Finished. |  | SCM | Splunk Cloud Modernization
[8 empty] | OBH | Observability Hub
[8 empty] | CAH | Cloud Automation + Helix
Themes and product areas come from the enterprise setup. Ask the Director to change them. | [7 empty] | CMG | Cloud Migration
[8 empty] | CAD | Cloud AD
[8 empty] | DVO | Cloud DevOps
[8 empty] | AGT | Agile Tools